## Activities
id | op | name | location | wtg_shutdown_dur | wec_shutdown_dur | pv_shutdown_dur | duration | hs | tp | ws | ws_hub | cs | light
- | - | - |  | - | - | - | hours | m | s | m/s | m/s | m/s | -
ACT101_01 | owc_OP101 | Transit to site | transit |  |  |  |  | 3 |  |  |  |  | FALSE
ACT101_02 | owc_OP101 | Vessel preparation | site |  |  |  | 2 | [5 empty] | FALSE
ACT101_03 | owc_OP101 | Mooring line replacement | site |  |  |  | 6 | 2 |  |  |  | 1 | FALSE
ACT101_04 | owc_OP101 | Transit to port | transit |  |  |  |  | 3 |  |  |  |  | FALSE
ACT102_01 | ofw_OP103 | Replace blade | port |  |  |  | 12 |  |  |  | 10 |  | FALSE
ACT103_01 | oce_OP110 | Transit to site | transit |  |  |  |  | 3 |  |  |  |  | FALSE
ACT103_02 | oce_OP110 | Cable repair | site |  |  |  | 8 | 1 | 12 | 20 |  | 1.5 | FALSE
ACT103_03 | oce_OP110 | Transit to port | transit |  |  |  |  | 3 |  |  |  |  | FALSE
CPO_A30_A1 | owc_removal_tow | Transit to site | transit |  |  |  |  | 3 |  |  |  |  | FALSE
CPO_A30_A2 | owc_removal_tow | WEC disconnect | site |  | 2 |  | 2 | 1.5 |  |  |  |  | TRUE
CPO_A30_A3 | owc_removal_tow | Tow to port | transit |  | TRUE |  |  | 2 |  |  |  |  | FALSE
CPO_A31_A1 | owc_redeploy_removal_tow | Tow to site | transit |  | TRUE |  |  | 2 |  |  |  |  | FALSE
CPO_A31_A2 | owc_redeploy_removal_tow | WEC connect | site |  | 2 |  | 2 | 1.5 |  |  |  |  | TRUE
CPO_A31_A3 | owc_redeploy_removal_tow | Transit to next device | site |  | 0 |  |  | 3 |  |  |  |  | FALSE
CPO_A31_A4 | owc_redeploy_removal_tow | WEC disconnect | site |  | 2 |  | 2 | 1.5 |  |  |  |  | TRUE
CPO_A31_A5 | owc_redeploy_removal_tow | Tow to port | transit |  | TRUE |  |  | 2 |  |  |  |  | FALSE
CPO_A33_A1 | owc_redeploy_tow | Tow to site | transit |  | TRUE |  |  | 2 |  |  |  |  | FALSE
CPO_A33_A2 | owc_redeploy_tow | WEC connect | site |  | 2 |  | 2 | 1.5 |  |  |  |  | TRUE
CPO_A33_A3 | owc_redeploy_tow | Transit to port | transit |  |  |  |  | 3 |  |  |  |  | FALSE
ACT110_01 | ofw_removal_tow | Vessel loading | port | 0 |  |  | 4 |  |  | 15 |  |  | FALSE
ACT110_02 | ofw_removal_tow | Transit to site | transit |  |  |  |  | 3 |  |  |  |  | FALSE
ACT110_03 | ofw_removal_tow | Disconnect WTG | site | 6 |  |  | 6 | [5 empty] | TRUE
ACT110_04 | ofw_removal_tow | Tow to port | transit | TRUE |  |  |  | 2 |  |  | 10 |  | FALSE
ACT111_01 | ofw_redeploy_removal_tow | Floating platform preparation | port | 8 |  |  | 8 | [5 empty] | FALSE
ACT111_02 | ofw_redeploy_removal_tow | Tow to site | transit | TRUE |  |  |  | 2 |  |  | 10 |  | FALSE
ACT111_03 | ofw_redeploy_removal_tow | Connect WTG | site | 6 |  |  | 6 | [5 empty] | TRUE
ACT111_04 | ofw_redeploy_removal_tow | Transit to next device | site | 0 |  |  |  | 3 |  |  |  |  | FALSE
ACT111_05 | ofw_redeploy_removal_tow | Disconnect WTG | site | 6 |  |  | 6 | [5 empty] | TRUE
ACT111_06 | ofw_redeploy_removal_tow | Tow to port | transit | TRUE |  |  |  | 2 |  |  | 10 |  | FALSE
ACT104_01 | ofw_redeploy_tow | Floating platform preparation | port | 8 |  |  | 8 | [5 empty] | FALSE
ACT104_02 | ofw_redeploy_tow | Tow to site | transit | TRUE |  |  |  | 2 |  |  | 10 |  | FALSE
ACT104_03 | ofw_redeploy_tow | Connect WTG | site | 6 |  |  | 6 | [5 empty] | TRUE
ACT104_04 | ofw_redeploy_tow | Transit to port | transit |  |  |  |  | 3 |  |  |  |  | FALSE